## Gantt
[20 empty] | Thanksgiving | Black Friday
Person | ID | Dependency | MILESTONE ID | DESCRIPTION | ESTIMATED HOURS | WORKED HOURS | DUE DATE | 2019-11-16 | 2019-11-17 | 2019-11-18 | 2019-11-19 | 2019-11-20 | 2019-11-21 | 2019-11-22 | 2019-11-23 | 2019-11-24 | 2019-11-25 | 2019-11-26 | 2019-11-27 | 2019-11-28 | 2019-11-29 | 2019-11-30 | 2019-12-01 | 2019-12-02 | 2019-12-03 | 2019-12-04 | 2019-12-05 | 2019-12-06 | 2019-12-07 | 2019-12-08 | 2019-12-09
Zach | 1 |  | GUI Skeleton | GUI displays with all buttons, text, images visible. | 10 | 0 | 2019-11-17 | 2019-11-16: 0
Jon | 2 |  | Display ECG | GUI loads ECG data and displays. Navigation possible. | 7.5 | 0 | 2019-11-19 | 2019-11-17: 0
| 3 | 2 | Detect R Peak | GUI detects and displays R-Peaks | 7.5 | 0 | 2019-11-22 | 2019-11-19: 0
| 4 |  | Visual Inspection | Share GUI with Lab for Visual Inspection | 1 | 0 | 2019-11-22
| 5 | 2 | Detect Squeeze | GUI loads Squeeze data. GUI detects Squeezes | 10 | 0 | 2019-11-22 | 2019-11-17: 0
| 6 | 2 | Save | GUI saves ECG and Squeeze detection data | 5 | 0 | 2019-11-25 | 2019-11-22: 0
| 7 | 6 | Pairing Algorithms | Pair and Analize per T-1000 and Classis | 10 | 0 | 2019-11-27 | 2019-11-23: 0
| 8 | 7 | User Interact | User is able to add R-Peaks, remove false-positives | 15 | 0 | 2019-11-29 | 2019-11-22: 0
| 9 |  | Visual Inspection | Share GUI with Lab for Interation review | 2 | 0 | 2019-11-29
| 10 | 8 | Save | Save analysis from Algorithms | 5 | 0 | 2019-11-30 | 2019-11-25: 0
| 11 |  | Plot | Save plots of ECG, Squeeze, Pair for trial | 10 | 0 | 2019-12-02 | 2019-11-28: 0
| 12 |  | Design Review | Share current version of GUI with Lab | 2 | 0 | 2019-12-02
| 13 |  | Deliver | Deliver all code, documentation. Install and verify. | 5 | 0 | 2019-12-09 | 2019-12-02: 0
[5 empty] | 90 | 0

## Graph
Expected | Worked | Expected | Sum Worked
10 | 0 | 10 | 0
7.5 | 0 | 17.5 | 0
7.5 | 0 | 25 | 0
1 | 0 | 26 | 0
15 | 0 | 41 | 0
2 | 0 | 43 | 0
10 | 0 | 53 | 0
5 | 0 | 58 | 0
10 | 0 | 68 | 0
5 | 0 | 73 | 0
10 | 0 | 83 | 0
2 | 0 | 85 | 0
5 | 0 | 90 | 0